## Levu Finance
| Function | Mandays
1 | Data Entry/Upload Screen for - Department's Cost (Operation cost) - Department's Support Cost (use for Production costing report) - business unit 's volume | 6
2 | Activities Tagging - Activities to Products and Business Units for Costing Allocation purposes. ** Assumption all activities is unique | 4
3 | Paramenters Setup Screen - Activity Costing Formula (able to set by multiple set then during report generate can choose which set of formula) - Support allocation cost to Product Formula - Business unit - Product | 4
4 | Report - Product Costing (filter by department) - Activity Costing (filter by department) (generate of report should not affect to Levu application during working time) | 8
5 | Activity Base Management - Cost | 8
6 | Activity Base Management - Trend | 4
7 | Product Costing Management - Product, Activity and volume | 4
| Product Costing Management - Trend | 4
| Requirement Study and FSD | 5
| SIT | 2
| UAT | 4
| Implementation | 1
| Production Support | 1
| Total | 55
| Cost: RM1200 | 66000
| GST | 3960
| Total Cost | 69960